## Sprint #2
Calculated Fields
Name | Product Backlog Item(s) | Description | Inicio | Fim | Milestone | Team | Priority (1=Low, 9=High) | Type | Category | Business Value | Risk | Status | Comments | Original Estimate (Hours) | New Estimate (Hours) | Change | Revised Value (Hours) | Amount Remaining (Hours) | Start | 2013-11-12 | 2013-11-13 | 2013-11-14 | 2013-11-15 | 2013-11-18
Caso de Uso Geral |  |  | 2013-11-12 | 2013-11-14 |  | Felippe | 9 | Artefatos | eBM | Alto |  | 2 - Concluído |  | 3 |  |  | 3 | 3
Especificação do Caso de Uso Geral |  |  | 2013-11-14 | 2013-11-18 |  | Laísa | 9 | Artefatos | eBM | Alto |  | 2 - Concluído |  | 5 |  |  | 5 | 5
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[13 empty] | Original | 8 |  | 0 | 8 | 8
[13 empty] | Revisado | 8 |  |  |  | Esforço Diário |  | 2 | 1 | 2 | 1 | 2
[13 empty] | Adicional | 0 |  |  |  | Esforço até data |  | 2 | 3 | 5 | 6 | 8
[13 empty] | % Aumentar | 0% |  |  |  | Esforço restante |  | 6 | 5 | 3 | 2 | 0
[18 empty] | % Remaining | 100% | 75% | 62.5% | 37.5% | 25% | 0%
[13 empty] | Remaining | 8
[13 empty] | % Remaining | 100% |  |  |  | Effort Change | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | Tam. Da equip | 2
[13 empty] | Esforço diario(est. @80%) | 0.625 |  |  | Validacao | 0
[17 empty] | Hoje | 2014-02-18 22:35
Note on A2: Randar Puust: Short name. Should be unique.
Note on B2: Randar Puust: This is a reference to the ID defined in the Product Backlog, if applicable.
Note on C2: Randar Puust: Longer description of the work item. If it references any external documents, they should be listed here.
Note on F2: Randar Puust: If there is a fixed date it needs to be done by.
Note on G2: Randar Puust: Who on the team has taken ownership of this work item.
Note on H2: Randar Puust: The priority. Items with a higher priority should be claimed first.
Note on I2: Randar Puust: What type of work item it is. Task - A new item Bug - A defect related to something that has already been completed. Impediment - Something that is holding back another team member and needs effort to finish.
Note on J2: Randar Puust: A category for the task. It is defined in the Lookup sheet.
Note on K2: Randar Puust: A ranking of the business value of this task. This can be used to prioritize a task.
Note on L2: Randar Puust: A ranking of the risk of this task. It can be used to prioritize a task.
Note on M2: Randar Puust: Current status of this task. This can be used to ensure multiple people do not work on the same task. The filter can also be used to filter out any tasks that have already been completed.
Note on N2: Randar Puust: Any additional comments or notes. It is a good practice to preface any comments with the author (e.g. RP)
Note on O2: Randar Puust: Esta é a estimativa de que foi descoberto no início do Sprint. Para as novas tarefas, este deve ser zero.
Note on P2: Randar Puust: Se a estimativa deve ser revista, ou é uma nova tarefa, o esforço está aqui.
Note on Q2: Randar Puust: This is the increase\decrease in hours that needs to be tracked
Note on R2: Randar Puust: Calculated field. It is the new estimate, if applicable.
Note on S2: Randar Puust: The amount of hours that are still remaining for this task. Should be zero for a task that is completed, and should never be negative. If it drops below zero, it should be re-estimated.
Note on T2: Randar Puust: This is here to make data entry a bit easier. Otherwise, you can't have a start of 100%
Note on U2: Randar Puust: This is the first day of the sprint. All of the other days are based on this.
Note on R29: Randar Puust: Este número deve ser zero. Se não for, você não adicionou um valor para a linha de novo esforço. Adicionar este montante a data de hoje.
Note on R30: Randar Puust: The date here affects when the Burn-down chart stops showing data and will change the formatting of todays date above.

## Lookups
Priority (1=Low, 9=High) | Business Value | Risk | Status | Type | Team | Category
1 | Baixo | Baixo | 1 - Em Andamento | Artefatos | Joelton | eBM
2 | Médio | Médio | 2 - Concluído | Codificação | Tayllan
3 | Alto | Alto |  |  | Felippe
4 |  |  |  |  | Laísa
5 |  |  |  |  | Rodrigo
6 | [6 empty] | 36 | OK
7 | [6 empty] | 0.3
8 | [6 empty] | 16 | OK
9 | [6 empty] | 4 | OK
10 | [6 empty] | 8
[7 empty] | 6 | OK
Note: To redefine a named value, go to Insert->Name->Define
Note on A1: Randar Puust: The priority. Items with a higher priority should be claimed first.
Note on B1: Randar Puust: A ranking of the business value of this task. This can be used to prioritize a task.
Note on C1: Randar Puust: A ranking of the risk of this task. It can be used to prioritize a task.
Note on D1: Randar Puust: Current status of this task. This can be used to ensure multiple people do not work on the same task. The filter can also be used to filter out any tasks that have already been completed.
Note on E1: Randar Puust: What type of work item it is. Task - A new item Bug - A defect related to soemthing that has already been completed. Impediment - Something that is holding back another team member and needs effort to finish.
Note on F1: Randar Puust: T4G: Who on the team has taken ownership of this work item.
Note on G1: Randar Puust: A category for the task. It is defined in the Lookup sheet.

## Sprint #2 - Retired
Calculated Fields
Name | Product Backlog Item | Description | Milestone | Team | Priority (1=Low, 9=High) | Type | Category | Business Value | Risk | Status | Comments | Original Estimate (Hours) | New Estimate (Hours) | Change | Revised Value (Hours) | Amount Remaining (Hours) | Start | 2007-06-01 | 2007-06-02 | 2007-06-05 | 2007-06-06 | 2007-06-07 | 2007-06-08 | 2007-06-09 | 2007-06-12 | 2007-06-13 | 2007-06-14 | 2007-06-15 | 2007-06-16 | 2007-06-19 | 2007-06-20 | 2007-06-21 | 2007-06-22 | 2007-06-23 | 2007-06-26 | 2007-06-27 | 2007-06-28 | 2007-06-29 | 2007-06-30
NÃO PLAN
NÃO PALN
Note on A2: T4G: Short name. Should be unique.
Note on C2: T4G: Longer description of the work item. If it references any external documents, they should be listed here.
Note on D2: T4G: If there is a fixed date it needs to be done by.
Note on E2: T4G: Who on the team has taken ownership of this work item.
Note on F2: T4G: The priority. Items with a higher priority should be claimed first.
Note on G2: T4G: What type of work item it is. Task - A new item Bug - A defect related to soemthing that has already been completed. Impediment - Something that is holding back another team member and needs effort to finish.
Note on M2: T4G: This is the estimate that was figured out at the beginning of the Sprint. For new tasks, this should be zero.
Note on N2: T4G: If the estimate needs to be revised, or it's a new task, the effort is here.
Note on O2: Randar Puust: This is the increase\decrease in hours that needs to be tracked
Note on P2: T4G: Calculated field. It is the new estimate, if applicable.
Note on S2: Randar Puust: This is the first day of the sprint. All of the other days are based on this.